## Project Planner
Project Bedbug Plan
| Status ( Current = *) | green |  | *
| SUB-TASK => |  |  |  |  | Current Period Highlight: |  | 9 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete | Actual (beyond plan) | % Complete (beyond plan)
| Additional Activityies can be added below main Activity with more detail and assigned owners | [6 empty] | Progress and Schedule | [12 empty] | Reading Week
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Milestones | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | % PERCENT COMPLETE | Owner ¦¦ Status | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | Additional Details/Notes
| Project description | 1 | 1 | 1 | 1 | 100% | [13 empty] | Assumption is that project description is complete as it was provided. More detail could be added in final project document.
| Requirement analysis | 2 | 2 | 2 | 2 | 100%
◆ | Requirement document | 3 | 4 | 3 | 2 | 30%
| System design for first version | 4 | 3 | 4 | 2 | 40%
◆ | System design Document | 5 | 3 | 5 | 2 | 0% | [13 empty] | note: Project Deliverable is single Document at end of term
◆ | Implementation for the first version | 7 | 2 | 7 | 3 | 0% | [13 empty] | Need UI and DB components to move forward. Even if not fully flushed out.
=> | Data Model and Source Control | 7 | 2 | 7 | 3 | 0% | Jeremy | [12 empty] | Delivered: build process for database on git Update: will work to provide DB model asap
=> | Class Architecture | 7 | 2 | 7 | 3 | 50% | Pierce | [12 empty] | Target Acheived: Class Skeleton layout on git Next Steps:Flush out methods for UI, Auth and DB - Report where help is required by team
=> | UI/UX Frontend | 7 | 2 | 7 | 3 | 0% | Dylan | [12 empty] | Target Deliverable: Design for Room Request screen on git Update:reported issues during team meeting - upload what you have and the team can look at it
=> | User Auth/Build Control/Quality | 7 | 2 | 7 | 3 | 50% | Richard | [12 empty] | Delivered - Clonable User Authentication on git NextSteps: Will provide extra details on how to build locally
| Testing the first version of the system | 9 | 2 | 9 | 2 | 0% | [13 empty] | Ideal target build for testing inlcudes DB, SignOn, Home Screen and Student Room Request. Admin aproval would be ideal but maybe too much
◆ | Complete the first version of the system | 9 | 1 | 9 | 2 | 0% | [13 empty] | Richard will attempt to mitigate schedule risk by drafting scope for Phase 2 while outstanding tech deliverables are completed by leads
| Requirement analysis for incremental | 9 | 2 | 9 | 3 | 0%
◆ | Design and implantation second version | 11 | 2 | 11 | 2 | 0%
◆ | Project report document | 10 | 3 | 11 | 2 | 0% | [13 empty] | Rick to provide update of shared version of document. Feel free to add anything pertinent.
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## Sheet1
Project description
Requirement analysis
Requirement document
System design for first version
System design Document
Implementation for the first version
Testing the first version of the system
Complete the first version of the system
Requirement analysis for incremental
Design and implantation second version
Project report document